## Sheet1
Start Date: August 22, 2016
Week: | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Document 1
Fergus | bar: 1 T to 2 W
Andrew | bar: 1 T to 2 W
Ryan | bar: 1 T to 2 W
Devidas | bar: 1 F to 2 W
Viraj | bar: 1 F to 2 W
Document 2
Fergus | bar: 2 T to 4 W
Andrew | bar: 2 T to 4 W
Ryan | bar: 2 T to 4 W
Devidas | bar: 2 T to 4 W
Viraj | bar: 2 T to 4 W
Document 3 | bar: 5 W to 5 F
Fergus: Gantt chart, FP, RTM | bar: 5 M to 5 F
Andrew: Use cases and diagrams | bar: 5 M to 5 F
Ryan: Use cases and diagrams | bar: 5 M to 5 F
Devidas: Use cases and diagrams | bar: 5 M to 5 F
Viraj: Use cases and diagrams | bar: 5 M to 5 F
2016-09-26
Week: | 1 M: 6; 2 M: 7; 3 M: 8; 4 M: 9; 5 M: 10
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Document 3 | bar: 6 M to 6 W
Fergus: Gantt chart, FP, RTM | bar: 6 M to 6 W
Andrew: Use cases and diagrams | bar: 6 M to 6 W
Ryan: Use cases and diagrams | bar: 6 M to 6 W
Devidas: Use cases and diagrams | bar: 6 M to 6 W
Viraj: Use cases and diagrams | bar: 6 M to 6 W
Document 4
Fergus: Gantt chart, WSD, RTM | bar: 6 F to 7 T
Andrew: Object design | bar: 6 F to 7 T
Ryan: Object design | bar: 6 F to 7 T
Devidas: Object design | bar: 6 F to 7 T
Viraj: Object design | bar: 6 F to 7 T
Document 5
Fergus: Rationale, Gantt, WSD | bar: 7 F to 8 T
Andrew
Ryan | bar: 8 M
Devidas
Viraj
Document 6
Fergus: Source Code, Test Case, | bar: 9 M to 10 W
RTM, Gantt, WSD
Andrew: Source Code, Test Case, | bar: 8 M to 8 T; 9 M to 10 W
COCOMO
Ryan: Source Code, Test Case | bar: 8 M to 8 T; 9 M to 10 W
Devidas: Source Code, Test Case | bar: 8 M to 8 T; 9 M to 10 W
Viraj: Source Code, Test Case | bar: 8 M to 8 T; 9 M to 10 W
Week: | 6 M: 11; 7 M: 12; 8 M: 13; 9 M: 14; 10 M: 15
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Presentation
Fergus: Preparation | bar: 13 M to 13 T
Andrew: Preparation | bar: 13 M to 13 T
Ryan: Preparation | bar: 13 M to 13 T
Devidas: Preparation | bar: 13 M to 13 T
Viraj: Slide Deck, Preparation | bar: 13 M to 13 T
Final Code
Fergus | bar: 11 M to 12 F; 14 M to 15 T
Andrew | bar: 11 M to 12 F; 14 M to 15 T
Ryan | bar: 11 M to 12 F; 14 M to 15 T
Devidas | bar: 11 M to 12 F; 14 M to 15 T
Viraj | bar: 11 M to 12 F; 14 M to 15 T
Final Document
Fergus | bar: 14 M to 15 T
Andrew | bar: 14 M to 15 T
Ryan | bar: 14 M to 15 T
Devidas | bar: 14 M to 15 T
Viraj | bar: 14 M to 15 T